## READ ME
Self-Assessment Capability Survey Form (SACS)
Guide for Users
Guidance Notes on the completion of the Self-Assessment Capability Survey Form
Purpose
The purpose of the SACS form is to assist Member States and the IAEA to understand the current situation which exists in a State in relation to its preparedness for response to a nuclear security event and so, if required by the State, to initiate the process for improvement of national nuclear security response capability. This instrument is designed to consider, in detail, each key element of preparedness for response. By completing the SACS, the State should be able to identify the specific areas in nuclear security response capabilities in which its preparedness is strong, as well as identifying areas for improvement, which need to be addressed.
Once all these areas for improvement have been identified, they can be prioritised by the State in an action plan (Capability Development Plan “CDP”), nationally endorsed and, if required, jointly signed by the IAEA. Proper implementation of such an action plan will ensure that the State acquires its effective nuclear security event response capability, proportional to its expectations and needs.
In addition, by following the SACS process it is hoped that Member States will be provided with a further opportunity to assimilate the recommendations of the IAEA with regard to the response to Nuclear Security Events.
As soon as a State commences completion of the SACS process, the SACS forms and the CDP should be treated as confidential.
Structure of the SACS
Experience has demonstrated that a State’s response to nuclear security events (and indeed to all types of security events) is far more effective when that response follows a recognised structure. A generic response structure is set out in the IAEA Nuclear Security Series publications and in particular in Section 4 of NST 004 (Draft) in the form of key response activities. These activities include (but are not limited to):
Information Gathering
Information Analysis
Notification, Activation and Deployment
Interdiction
Criminal Investigations
Public Information
Consequence Management
The SACS follows this same structure, enabling a State to examine each Key Response Activity and Action of its response capabilities in detail. Additionally, the SACS refers to a number of overarching capabilities around National Response Plans and the issues of Command and Control which, although not a key activity per se, are essential if a State’s key activities are to be undertaken in a coordinated manner.
Grading Capabilities with Performance Indicators
In order to assist a State in completing the SACS a grading structure has been developed. This structure takes the form of Performance Indicators, designed to enable a State to assess its current capabilities against a ‘sliding scale’ of preparedness. This scale is graded from 0-3, with 0 indicating no capability in a particular area, and 3 indicating well-developed and tested capability which requires no further development in order to reach an effective level.
Each Performance Indicator contains a short definition and some examples of possible indicators, which may assist a State to determine the most appropriate grade. The SACS Performance Indicators are set out in Table below.
In addition to enabling a State to identify and prioritize nuclear security response activities, it is foreseen that the use of these Performance Indicators will enable the IAEA to target its resources more effectively by identifying Member States who have common capability requirements. IAEA may then offer the identified capability development support to these States, where appropriate, in a group setting (for example by running regional workshops for States who have identified the same needs within a region).
An additional benefit of such an approach may be to enable States with similar needs to cooperate regionally, providing enhanced regional capabilities and offering support to each other as they develop their capabilities.
Completion of the SACS
NST 004 recommends the use of multi-agency workshops or meetings for States wishing to develop their National Framework for Managing the Response to Nuclear Security Events. The same approach is also recommended when completing the SACS. A multi-Agency workshop or meeting enables national stakeholders to discuss their capabilities with partners, identifying the areas of strength and areas of developmental need, and reaching an agreed assessment of capability when completing each SACS category. This assessment of capability should then be recorded in the appropriate SACS category as a grade in accordance with the Performance Indicators outlined above.
In addition to the assignment of a Performance Indicator grade for each SACS question, States are encouraged to provide some brief comments rationalising their assessment of performance. These comments are especially important where a State allocates a grade of 0 or 3, assisting the IAEA with determining the level of support required by the State to commence development of capability, or the State’s ability to support other States in this area.
An example of a completed SACS (based on a fictitious State) can be found at Annex 1. This example should be seen only as an indication of the type of comments which can be used to support a particular grading. Each State will clearly wish to use its own comments when completing its SACS.
Next Steps - Capability Development Planning
Once a State has completed its SACS process and developed a prioritised draft Capability Development Plan (CPD) the CDP may be forwarded to the IAEA for consultation, evaluation and an assessment of need to take place, in order to discuss the completion of a Capability Development Plan for the State. The Capability Development Plan should be endorsed nationally and may be signed jointly between the State and the IAEA. and will set out a structured, prioritised plan for the development of the State’s nuclear security response capability, in accordance with the priorities highlighted during the SACS process
NEXT PAGE
NEXT PAGE

## Legoland
No. | Key Activity | Response Action | PI Grade | Comments
1) Overarching Capabilities
O-1 | Multi-Agency Command, Control and Coordination | All agencies to be involved in response to NSE identified | 2 | Legoland has identified the key first response and scientific agencies involved in the response but needs to do further work to identify supporting agencies such as utilities companies and transportation organisations. This work is in progress and the update is expected in the next 12 months
O-2 |  | Lead organization designated | 2 | The Legoland Nuclear Commission (LNC) has been identified as the lead agency for the response to Nuclear Security Events. After discussion however we recognise that this needs to be amended to enable the Legoland police to take the lead. We have tasked our Police Chief to create a formal Agreement which will state that the Police are in charge.
O-3 |  | Roles and responsibilities assigned | 1 | The roles and responsibilities for the responding agencies are understood by all but they are not formally recorded anywhere
O-4 |  | Relations between all competent authorities involved in response to NSE are defined through formal protocols (e.g. written agreements or memoranda of understanding) including policy/strategic, tactical and operational levels [4.15, 4.17] | 0 | No formal agreements exist at this time
O-X | Additional written comments: | Note: Additional written comments to be used when designing Country’s Action Plan. We recognise the need to formalise the relationships between the responding agencies to reduce the risk of conflict or duplication of effort. This will be a priority for us in our CDP, so that such relationships are clear when the NRP is created.
2) Key Response Activities
IG-1 | Information gathering | Collect information on alarms and alerts | 2 | We have a telephone network to gather such information but would like to develop a live monitoring system in the near future.
IG-2 |  | Collect information about material, adversary and/or target. | 2 | The Legoland Nuclear Commission can provide information on materials, although this is not formally agreed anywhere. The National Counter-Terrorist Analysis Centre will collect information on adversaries and targets as required
IG-3 |  | Confirm status of event: e.g. ongoing; stand-off; adversaries neutralised | 2 | The National Counter-Terrorist Analysis Centre provide all such information through their communications network to, for example, Local Police departments.
IG-4 |  | Confirm amount and nature of nuclear or other radioactive material | 3 | Legoland Nuclear Commission has a full inventory of all nuclear and radioactive material. This is regularly updated and can be accessed 24/7 from their control centre.
IG-5 |  | Gather relevant intelligence | 2 | The National Counter-Terrorist Analysis Centre will gather intelligence as required
IG-X | Additional written comments:
IA-1 | Information analysis | Assess, confirm and validate alarms and alerts | 2 | We have standard operating procedures for all technical agencies, but nothing in relation to the assessment of information alerts.
IA-2 |  | Assess possible adversaries and associated networks | 3 | The NCTAC has the ability fo fully analyse any such adversaries and / or networks
IA-3 |  | Protect sensitive information | 1 | All Law Enforcement agencies have information security measures in place but there are no plans to extend these to other partner agencies
IA-4 |  | Share appropriate information with partners | 1 | Information can be shared but there are no formal protocols in place between partner agencies and no plans to develop any at this time
IA-5 |  | Assess the initial situation (adversary, method, nature of material involved, material stationary or in transit) | 2 | This assessment will be carried out jointly by the LNC and NCTAC. Both are qualified in their respective fields, although they have never worked together before. An exercise testing the two agencies’ ability to work together is planned for early next year.
IA-6 |  | Determine nuclear security event type (i.e. Type 1, Type 2 or Type 3) | 2 | LNC would be tasked with this determination. There is training planned on the development of a Framework for the management of nuclear security events, after which LNC will be fully trained to carry out this work.
IA-7 |  | Monitor and review the ongoing Nuclear Security Event | 1 | LNC will be tasked to do this. Their ability has not yet been tested and there are no plans to test this in the near future.
IA-8 |  | Estimate potential consequences (health, economic, societal and environment) | 2 | We have no formal organisation able to do this. We would rely on our various ministries working together. This has never been tested.
IA-9 |  | Assess possibility of multiple events or escalation of event type | 1 | We would ask NCTAC to do this
IA-10 |  | Assess potential international impact (for example impact on shipping and cross-border movement of goods or people) | 0 | We have no process to do this at this time
IA-11 |  | Identify appropriate response resources to deploy (considering graded approach) | 1 | We would rely on the responding agencies to tell us what they needed. We have no formal processes for this and no plans to develop anything at this time
IA-12 |  | Reassess as more information is received | 1 | We would ask NCTAC to do this
IA-X | Additional written comments: | We need to prioritise some of these areas as we have little tested capability in the assessment of multiple events, cross-border impact or resource identification
NA-1 | Notification, activation and deployment [2] | Notify relevant organizations | 1 | We would notify our responders through the normal means. There is no formal process to notify specialist agencies.
NA-2 |  | Activate relevant organizations | 1 | See NA-1 above
NA-3 |  | Activate relevant response plans (eg contingency plans, emergency plans and/or national plans | 1 | We have appropriate facility plans but no NRP for NSEs at this time
NA-4 |  | Deploy radiation monitoring teams | 2 | LNC have teams designated to deploy to all emergencies involving radiation. This deployment would include NSEs
NA-5 |  | Establish predetermined multi-agency integrated response command structure at all levels (strategic, tactical and operational levels). | 2 | We have a tested command structure for natural disasters and major events. We would use this structure for NSEs. An exercise to test this structure against an NSE is planned in the next 18 months
NA-6 |  | Deploy appropriate resources | 1 | We have no formal resource deployment plans. Deployment is based on the requirement at the time. There are no plans for the deployment of specialist agencies (such as NRC response team)
NA-7 |  | Reinforce security measures and activities at strategic locations | 1 | We have no formal plans or procedures to initiate this process at this time
NA-8 |  | Create awareness and share information on the status of the event with all response organizations | 1 | We have no formal process to share situational awareness between agencies
NA-9 |  | Request international cooperation and assistance as necessary | 2 | We have a good relationship with our neighbouring countries and have helped each other to respond to natural disasters in the past. WE have a cross-border exercise planned for flooding in three months’ time. The plans for this type of disaster can be used to request assistance for NSEs
NA-X | Additional written comments: | The completion of a CDP and creation of an NRP is a priority for us at this time
I-1 | Interdiction (Counteraction) | Disrupt an ongoing NSE | 1 | We have no specialist capability to disrupt an ongoing NSE unless it is only relating to trafficking or information alerts
I-2 |  | Reinforce security measures at the scene | 0 | We have a bomb squad but they do not have any CBRN capability or experience
I-3 |  | Obtain functional control of device, material and / or adversary | 0 | Very difficult with no specialist capabilities
I-4 |  | Render safe the device (as applicabke) | 3 | We have a bomb squad but they do not have any CBRN expreience.
I-5 |  | Take necessary steps to gain control of seized material | 0 | See I-3 above
I-6 |  | Take necessary steps to protect target, set equipment and vital areas | 2 | We have processes in place to protect these areas
I-X | Additional written comments: | The creation of a team to deal with CBRN devices is a priority for us at this time
CI-1 | Criminal investigations | Collect evidence associated with NSE | 2 | Police can do this, as they are responsible for all evidence collection
CI-2 |  | Implement radiological crime scene management (as applicable) | 0 | We have no specialist police teams trained or equipped to deal with radiological crime scenes
CI-3 |  | Expert eyewitness and expert witness testimony | 3 | Legoland Police will deal with eyewitnesses, LNC will provide experts as needed
CI-4 |  | Maintain integrity of evidence and ensure chain of custody | 3 | Police responsibility
CI-5 |  | Conduct Conventional and nuclear forensics | 2 | LNC can do this, supported by IAEA
CI-6 |  | Support prosecution | 3 | Police responsibility
CI-X | Additional written comments: | The police need the ability to work in a radiological crime scene. We cannot train or equip them to do this and will need to seek external assistance. This is a priority for us.
PI-1 | Public information | Release information to the public [17, 18] | 3 | Ministry of Public Information will manage this
PI-2 |  | Gather information from the public | 3 | See PI-1
PI-3 |  | Provide advice to the public | 3 | See PI-1
PI-4 |  | Reassure the public | 3 | See PI-1
PI-X | Additional written comments:
CM-1 | Mitigate Consequences [3] | Restrict publice access to the scene(s) | 1 | Police will do this
CM-2 |  | Package, transport and store radioactive material | 0 | LNC will be tasked to do this, as they are responsible for the management of all radioactive and nuclear materials within the country
CM-3 |  | Restore normality | 3 | We have no plans to do this and it is not clear who will be responsible for this
CM-3 | Additional written comments:
P-1 | National Response Plan | National Response Plan for NSE is in place | 1 | We have no NRP at this time, but plan to develop one after we have completed the CDP phase of its development
P-X | Additional written comments:
NOTES:
[1] Taking into account references [8, 9, 16, 18, 25].
[2] In case of a nuclear or radiological emergency triggered by a nuclear security event, the following references apply for identifying respective emergency response actions related to notification and activation: [8], [12], [16] and [25]. In this case, notification may also be necessary emergency response action on an international level within the framework of Early Notification Convention [27] and its operational tool- EPR-IEComm [28].
[3] Refs [7], [9–22] and [25] provide guidance on other emergency responses action related to consequence management of a nuclear or radiological emergency triggered by a nuclear security event.

## 1-SACS
No. | Key Activity | ` | PI Grade | Comments
1) Overarching Capabilities
O-1 | Multi-Agency Command, Control and Coordination | All agencies to be involved in response to NSE identified
O-2 |  | Lead organization designated
O-3 |  | Roles and responsibilities assigned
O-4 |  | Relations between all competent authorities involved in response to NSE are defined through formal protocols (e.g. written agreements or memoranda of understanding) including policy/strategic, tactical and operational levels [4.15, 4.17]
O-X |  | Additional written comments (any other area for improvement): | NA
2) Key Response Activities
IG-1 | Information gathering | Collect information on alarms and alerts
IG-2 |  | Collect information about material, adversary and/or target.
IG-3 |  | Confirm status of event: e.g. ongoing; stand-off; adversaries neutralised
IG-4 |  | Confirm amount and nature of nuclear or other radioactive material
IG-5 |  | Gather relevant intelligence
IG-X |  | Additional written comments (any other area for improvement): | NA
IA-1 | Information analysis | Assess, confirm and validate alarms and alerts
IA-2 |  | Assess possible adversaries and associated networks
IA-3 |  | Protect sensitive information
IA-4 |  | Share appropriate information with partners
IA-5 |  | Assess the initial situation (adversary, method, nature of material involved, material stationary or in transit)
IA-6 |  | Determine nuclear security event type (i.e. Type 1, Type 2 or Type 3)
IA-7 |  | Monitor and review the ongoing Nuclear Security Event
IA-8 |  | Estimate potential consequences (health, economic, societal and environment)
IA-9 |  | Assess possibility of multiple events or escalation of event type
IA-10 |  | Assess potential international impact (for example impact on shipping and cross-border movement of goods or people)
IA-11 |  | Identify appropriate response resources to deploy (considering graded approach)
IA-12 |  | Reassess as more information is received
IA-X |  | Additional written comments (any other area for improvement): | NA
NA-1 | Notification, activation and deployment [2] | Notify relevant organizations
NA-2 |  | Activate relevant organizations
NA-3 |  | Activate relevant response plans (eg contingency plans, emergency plans and/or national plans
NA-4 |  | Deploy radiation monitoring teams
NA-5 |  | Establish predetermined multi-agency integrated response command structure at all levels (strategic, tactical and operational levels).
NA-6 |  | Deploy appropriate resources
NA-7 |  | Reinforce security measures and activities at strategic locations
NA-8 |  | Create awareness and share information on the status of the event with all response organizations
NA-9 |  | Request international cooperation and assistance as necessary
NA-X |  | Additional written comments (any other area for improvement): | NA
I-1 | Interdiction (Counteraction) | Disrupt an ongoing NSE
I-2 |  | Reinforce security measures at the scene
I-3 |  | Obtain functional control of device, material and / or adversary
I-4 |  | Render safe the device (as applicabke)
I-5 |  | Take necessary steps to gain control of seized material
I-6 |  | Take necessary steps to protect target, set equipment and vital areas
I-X |  | Additional written comments (any other area for improvement): | NA
CI-1 | Criminal investigations | Collect evidence associated with NSE
CI-2 |  | Implement Radiological Crime Scene Management (as applicable)
CI-3 |  | Obtain Eyewitness and Expert witness testimony
CI-4 |  | Maintain integrity of evidence and ensure chain of custody
CI-5 |  | Conduct Conventional and nuclear forensics as needed
CI-6 |  | Support prosecution
CI-X |  | Additional written comments (any other area for improvement): | NA
PI-1 | Public information | Release information to the public
PI-2 |  | Gather and analyse information from the public
PI-3 |  | Provide advice to the public
PI-4 |  | Reassure the public
PI-X |  | Additional written comments (any other area for improvement): | NA
CM-1 | Mitigate Consequences [3] | Restrict public access to scene(s)
CM-2 |  | Package, transport and store nuclear and other radioactive material
CM-3 |  | Restore normality
CM-X |  | Additional written comments (any other area for improvement): | NA
P-1 | National Response Plan | National response plan for nuclear security event is in place
P-X |  | Additional written comments (any other area for improvement): | NA
NOTES:
[1] Taking into account references [8, 9, 16, 18, 25].
[2] In case of a nuclear or radiological emergency triggered by a nuclear security event, the following references apply for identifying respective emergency response actions related to notification and activation: [8], [12], [16] and [25]. In this case, notification may also be necessary emergency response action on an international level within the framework of Early Notification Convention [27] and its operational tool- EPR-IEComm [28].
[3] Refs [7], [9–18] and [24] provide guidance on other emergency responses action related to consequence management of a nuclear or radiological emergency triggered by a nuclear security event.

## 2-Assessment Grid
| RESPONSE ACTIONS | SACS Overall PI Grade | SACS Comment | Policy | Procedures | Organization | Logistics | Infrastructure | Equipment | Personnel | Information | Training
Overarching Capabilities
O | Multi-Agency Command, Control and Coordination
O-1 | All agencies to be involved in response to NSE identified | 0 | 0
O-2 | Lead organization designated | 0 | 0
O-3 | Roles and responsibilities assigned | 0 | 0
O-4 | Relations between all competent authorities involved in response to NSE are defined through formal protocols (e.g. written agreements or memoranda of understanding) including policy/strategic, tactical and operational levels [4.15, 4.17] | 0 | 0
O-X | Additional task | NA | 0
Key Response Activities
IG | Information Gathering
IG-1 | Collect information on alarms and alerts | 0 | 0
IG-2 | Collect information about material, adversary and/or target. | 0 | 0
IG-3 | Confirm status of event: e.g. ongoing; stand-off; adversaries neutralised | 0 | 0
IG-4 | Confirm amount and nature of nuclear or other radioactive material | 0 | 0
IG-5 | Gather relevant intelligence | 0 | 0
IG-X | Additional task | NA | 0
Information Analysis
IA-1 | Assess, confirm and validate alarms and alerts | 0 | 0
IA-2 | Assess possible adversaries and associated networks | 0 | 0
IA-3 | Protect sensitive information | 0 | 0
IA-4 | Share appropriate information with partners | 0 | 0
IA-5 | Assess the initial situation (adversary, method, nature of material involved, material stationary or in transit) | 0 | 0
IA-6 | Determine nuclear security event type (i.e. Type 1, Type 2 or Type 3) | 0 | 0
IA-7 | Monitor and review the ongoing Nuclear Security Event | 0 | 0
IA-8 | Estimate potential consequences (health, economic, societal and environment) | 0 | 0
IA-9 | Assess possibility of multiple events or escalation of event type
IA-10 | Assess potential international impact (for example impact on shipping and cross-border movement of goods or people) | 0 | 0
IA-11 | Identify appropriate response resources to deploy (considering graded approach) | 0 | 0
IA-12 | Reassess as more information is received
IA-X | Additional task
NA | Notifiction, activation, deployment
NA-1 | Notify relevant organizations | 0 | 0
NA-2 | Activate relevant organizations | 0 | 0
NA-3 | Activate relevant response plans (eg contingency plans, emergency plans and/or national plans | 0 | 0
NA-4 | Deploy radiation monitoring teams | 0 | 0
NA-5 | Establish predetermined multi-agency integrated response command structure at all levels (strategic, tactical and operational levels). | 0 | 0
NA-6 | Deploy appropriate resources | 0 | 0
NA-7 | Reinforce security measures and activities at strategic locations | 0 | 0
NA-8 | Create awareness and share information on the status of the event with all response organizations | 0 | 0
NA-9 | Request international cooperation and assistance as necessary | 0 | 0
NA-X | Additional task | NA | 0
I | Interdiction (Counteraction)
I-1 | Disrupt an ongoing NSE | 0 | 0
I-2 | Reinforce security measures at the scene | 0 | 0
I-3 | Obtain functional control of device, material and / or adversary | 0 | 0
I-4 | Render safe the device (as applicabke) | 0 | 0
I-5 | Take necessary steps to gain control of seized material | 0 | 0
I-6 | Take necessary steps to protect target, set equipment and vital areas | 0 | 0
I-X | Additional task
CI | Criminal Investigation
CI-1 | Collect evidence associated with NSE | 0 | 0
CI-2 | Implement Radiological Crime Scene Management (as applicable) | 0 | 0
CI-3 | Obtain Eyewitness and Expert witness testimony | 0 | 0
CI-4 | Maintain integrity of evidence and ensure chain of custody | 0 | 0
CI-5 | Conduct Conventional and nuclear forensics as needed | 0 | 0
CI-6 | Support prosecution | 0 | 0
CI-X | Additional task | NA | 0
PI | Pulblic Information
PI-1 | Release information to the public | 0 | 0
PI-2 | Gather and analyse information from the public | 0 | 0
PI-3 | Provide advice to the public | 0 | 0
PI-4 | Reassure the public | 0 | 0
PI-X | Additional task | NA | 0
CM | Mitigate Consequences
CM-1 | Restrict public access to scene(s) | 0 | 0
CM-2 | Package, transport and store nuclear and radioactive material | 0 | 0
CM-3 | Restore normality | 0 | 0
CM-X | Additional task | NA | 0
P | National Response Plan
P-1 | National response plan for nuclear security event is in place | 0 | 0
P-X | Additional task | NA | 0
Response Actions - Capability Elements Grading

## 3-O
No. | Response Action | Element to be addressed |  |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE | SACS Comment |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
O-1 | All agencies to be involved in response to NSE identified | Policy | 0 | sem by se mel zase nakopirovat identifikovany problem | Ensure policy is in place to authorize any newlz identified organisation (O-1, Organisation) | NSC |  |  |  | x | x | x
|  | Procedures | 0
|  | Organization | 0 |  | Identify any missing organisation that should be involver in response to NSE | RPAZ
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
O-2 | Lead organization designated | Policy | 0 |  | Policy to be completed | NSC
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
O-3 | Roles and responsibilities assigned | Policy | 0
|  | Procedures | 0 |  | Formalize roles and responsibilities and relations between all involved organisations | NSC
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
O-4 | Relations between all competent authorities involved in response to NSE are defined through formal protocols (e.g. written agreements or memoranda of understanding) including policy/strategic, tactical and operational levels [4.15, 4.17] | Policy | 0
|  | Procedures | 0 |  | Develop SOPs and protocols for cooperation between or
|  | Organization | 0 |  | Formalize relationships between organisations | NSC
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
O-X | Additional written comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
CDP: Overarching Capability "O" - Multi-Agency Command, Control and Coordination

## 4-IG
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
IG-1 | Collect information on alarms and alerts | Policy | 0
|  | Procedures | 0 | Develop procedures specifically to collect information about information alerts | TBD
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program incl. exercises | RPAZ + IAEA
IG-2 | Collect information about material, adversary and target | Policy | 0
|  | Procedures | 0 | Establish procedures for confirming information specific to NSEs | State Security
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program incl. exercises on confirming information specific to NSEs | State Security +RPAZ
IG-3 | Confirm status of event: e.g. ongoing; stand-off; adversaries neutralised | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0 | NA | NA
|  | Training | 0 | Establish a training program incl. exercises that will ensure awareness among all stakeholders
IG-4 | Confirm nuclear material inventory / radioactive material registry. | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Provision of detection equipment for borders and for MEST | RPAZ + IAEA
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program incl. exercises that will improve confidence in border security duties | RPAZ + IAEA
IG-5 | Gather relevant intelligence | Policy | 0 | Review current policies in regards to inteligence gathering to ensure that nuclear security issues are included | State security
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish nuclear security awareness training program for inteligence gathering personel | RPAZ
IG-X | Additional written comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
Note on AB3: Any comment on dates or reference to an annex confirming dates later that 2020
Key Activity - Information Gathering
CDP: Key Activity - Information Gathering

## 5-IA
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
IA-1 | Assess, confirm and validate alarms and alerts | Policy | 0
|  | Procedures | 0 | Finalize the draft protocols for alarms | RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program on assessment of alarms Establih radiation awareness raising program for relevant medical services | RPAZ
IA-2 | Assess possible adversaries and associated networks | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish nuclear security awareness training for inteligence services and police | RPAZ
IA-3 | Protect sensitive information | Policy | 0
|  | Procedures | 0 | Identify all involved organisations and Develop procedures for them | GPSI, RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop a training program on protectionn of nuclear security specific information | GPSI, RPAZ
IA-4 | Share information with partners | Policy | 0
|  | Procedures | 0 | Develop procedures, protocols for information sharing about nuclear security and integrate them into existing framework | Establish a working group (Police, Inteligence, Defence, Forensics dept., RPAZ, Customs)
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
IA-5 | Assess the initial situation (adversary, method, nature of material involved, material stationary or in transit) [3.4-7] | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Fully equipped MEST vehicle | RPAZ
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program for initial assessment | RPAZ, Inteligence
IA-6 | Determine nuclear security event type (i.e. Type 1, Type 2 or Type 3) | Policy | 0
|  | Procedures | 0 | Develop procedures | RPAZ, Inteligence
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop a training program on determination of nuclear security event type | RPAZ, Inteligence
IA-7 | Monitor and review the ongoing Nuclear Security Event | Policy | 0
|  | Procedures | 0 | Deevelop a frameg work (document) that describes roles and responsibilities for monitoring ongoing NSE and integrate in the national response plan for NSEs | NSC, RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
IA-8 | Estimate potential consequences (health, economic, societal and environment) | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish multi-agency exercise program including all aspects of information analysis (IA-9, e.g.) | RPAZ
IA-9 | Assess possibility of multiple events or escalation of event type | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
IA-10 | Assess potential international impact (for example impact on shipping and cross-border movement of goods or people) | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish multi-agency exercise program including international impacts and multiple events | RPAZ
IA-11 | Identify appropriate response resources to deploy (considering graded approach) | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop a training program on all aspects of response to NSE, including graded aprocha | RPAZ
IA-12 | Reassess as more information is received | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
IA-X | Additional written comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
CDP: Key Activity - Information analysis

## 6-NA
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
NA-1 | Notify relevant organizations | Policy | 0
|  | Procedures | 0 | Develop procedures and integrate with existing ones | Police, Civil protection, RAPZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program | Police, Civil protection, RAPZ
NA-2 | Activate relevant organizations | Policy | 0
|  | Procedures | 0 | Develop procedures and integrate with existing ones | Police, Civil protection, RAPZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program | Police, Civil protection, RAPZ
NA-3 | Activate relevant response plans (eg contingency plans, emergency plans and/or national plans | Policy | 0
|  | Procedures | 0 | Develop procedures and integrate with existing ones | Police, Civil protection, RAPZ, Forensics dept.
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish a training program | Police, Civil protection, RAPZ, Forensics dept.
NA-4 | Deploy radiation monitoring teams | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Assessing requirement for total number of MESTeams Fully equipped MEST vehicle | RPAZ
|  | Personnel | 0 | Identify the need for additional personel for MESTs and implement | RPAZ
|  | Information | 0
|  | Training | 0 | Establish a MEST training program + regular multi-agency NSE exercises | RPAZ
NA-5 | Establish predetermined multi-agency integrated response command structure at all levels (strategic, tactical and operational levels). | Policy | 0
|  | Procedures | 0 | Develop procedures
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establisha training program to embed new procedures
NA-6 | Deploy appropriate resources | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop and conduct nuclear security exercise to test the capability to deploy nuclear resources | Working group (all involved organisation)
NA-7 | Reinforce security measures and activities at strategic locations | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Assess required types and number of radiation detection equipment obtain | RPAZ, Police, Defence
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
NA-8 | Create awareness and share information on the status of the event with all response organizations | Policy | 0
|  | Procedures | 0 | Develop procedures from lessons learned from the exercise (NA-8, Training) | Working group (all involved organisation)
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | To develop and undertake exercise to test disaster response procedures against NSE exercice scenario | Working group (all involved organisation)
NA-9 | Request international cooperation and assistance as necessary | Policy | 0
|  | Procedures | 0 | Develop procedures from lessons learned from the exercise (NA-8, Training) | Working group (all involved organisation)
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Undertake exercise to test disaster response procedures against NSE exercice scenario | Working group (all involved organisation)
NA-X | Additional written comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
CDP: Key Activity - Notification, activation and deployment

## 7-I
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Recommended Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
I-1 | Disrupt an ongoing NSE | Policy | 0 | Assign roles and responsibilities to the organisatrions involved in disrupting an NSE | Police to take this forward recommended - RPAZ to lead discussion at the NSC
|  | Procedures | 0 | Develop and agree SOPs
|  | Organization | 0 | Develop inter-agency structure for co-operation with agreed protocols
|  | Logistics | 0 | Provide appproporaiate vehicels for the response teams
|  | Infrastructure | 0
|  | Equipment | 0 | Provide approopriate equipment
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop and uimplement a training programme for the multi-agency personnel who will deal the the NSE | Police, Military and Fire Service
I-2 | Reinforce security measures at the scene | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Provision of equipment for staff carrying out the containment
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
I-3 | Obtain functional control of material and threat components | Policy | 0 | Establish policy for which agency with carry out this task | see above
|  | Procedures | 0 | Develop SOPs
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Provide apporoporiate equipmenty
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop training programme to enable personnel to effectvely use equipment and to follow SOPs
I-4 | Render safe the device (as applicable) | Policy | 0 | Establish policy for which agency with carry out this task
|  | Procedures | 0 | Develop SOPs
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Provde appropriate equipment
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop training programme to enable personnel to effectvely use equipment and to follow SOPs
I-5 | Take necessary steps to gain control of seized material | Policy | 0
|  | Procedures | 0 | Develop SOPs
|  | Organization | 0
|  | Logistics | 0 | Provide specilaist vehicles
|  | Infrastructure | 0 | Design and construct storage facilities
|  | Equipment | 0 | Identify and provide appropriate equipment
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop training programme to enable personnel to effectvely use equipment and to follow SOPs
I-6 | Take necessary steps to protect target, set equipment and vital areas | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Identify and provide appropriate equipment
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
I-X | Additional written comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
CDP: Key Activity - Interdiction/Counteraction

## 8-CI
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
CI-1 | Collect evidence associated with NSE | Policy | 0
|  | Procedures | 0 | Develop SOPs in respect of handlinig radioligical crime scene | RPAZ + Forensics Dept
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0 | Assess requirement for and construct storage facilities | RPAZ + Forensics Dept
|  | Equipment | 0 | Assess the type of equipment needed and procure | RPAZ + Forensics Dept
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Design and implement training programme | RPAZ + Forensics Dept
CI-2 | Implement Radiological Crime Scene Management (as applicable) | Policy | 0
|  | Procedures | 0 | Implement IAEA guidance on RCM | Police and Forensics Dept with support from RPAZ
|  | Organization | 0 | Draft and agree inter-agency agreements and plans | Police and Forensics Dept with support from RPAZ
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Assess the type of equipment needed and procure | RPAZ + Forensics Dept
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Design and implement training programme | RPAZ + Forensics Dept
CI-3 | Obtain Eyewitness and Expert witness testimony | Policy | 0
|  | Procedures | 0 | Create procedxures and draw up lists of expert witnesses who are recognised by the court | Police with RPAZ support - intelligence service to be involved
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0 | As in procedures | As in procedures
|  | Training | 0
CI-4 | Maintain integrity of evidence and ensure chain of custody | Policy | 0
|  | Procedures | 0 | Develop SOPs in respect of handlinig radiological crime scene evidence | Forensics Dept with supprt from RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0 | Assess requirement for and construct storage facilities
|  | Equipment | 0 | Identify requirement fo and provide suitable containment and packaging
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop and implement appropriate training progarmme | Forensics Dept with supprt from RPAZ
CI-5 | Conduct Conventional and nuclear forensics | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Identify requirement for nuclear forensics equipment and provide | Forensics Dept with supprt from RPAZ
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish and implement training programme | Forensics Dept with supprt from RPAZ
CI-6 | Support prosecution | Policy | 0
|  | Procedures | 0 | Develop procedures for the presentation of RCM evidcence in court | National Prosecuting Authority, Police, Forensics Dept, RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Develop awareness-raising events for prosaecutors and the legal representatives and judiciary | NPA, Forensics Dept and RPAZ
CI-X | Additional comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
Key Activity - Criminal investigations
CDP: Key Activity - Criminal Investigation

## 9-PI
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
PI-1 | Release information to the public [17, 18]. | Policy | 0
|  | Procedures | 0 | Develop procedures and protocols for releasing NSE info to the public, for example specific information relating to materials or hazards | Ministry of Information, Police, RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
PI-2 | Gather information from the public | Policy | 0
|  | Procedures | 0 | Assess the requirements (consider organizing meeting of involved organisations or table top exercise) | Police, Inteligence, RPAZ, Ministry of Media
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
PI-3 | Provide advice to the public | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0 | Assess the requirements | Police, Inteligence, RPAZ, Ministry of Media
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Provide training on informing public in case of radiation emergency (radiation safety event) | RPEZ (IAEA to provide)
PI-4 | Reassure the public | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0 | Assess the requirements | Police, Inteligence, RPAZ, Ministry of Media
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
PI-X | Additional comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
Key Activity - Public information
CDP: Key Activity - Public Information

## 10-CM
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
CM-1 | Restrict public access to the scene(s) | Policy | 0
|  | Procedures | 0 | Establish procedures on restricting public access to the radiological scene(s) | Police, RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish training program on restricting public access to the radiological scene(s) + radiation fundamentals awareness training for law enforcement | Police, RPAZ
CM-2 | Package, transport and store radioactive material | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0 | see CI | see CI
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
CM-3 | Restore normality | Policy | 0
|  | Procedures | 0 | Develop SOPs | Police, RPAZ
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0 | Enure decontamination capability for nuclear security operations | RPAZ, Fire brigade
|  | Personnel | 0
|  | Information | 0
|  | Training | 0 | Establish training program on restoring normality | Police, RPAZ
CM-X | Additional written comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020
Key Activity - Consequence management[3]
CDP: Key Activity - Mitigate Consequences

## 11-P
No. | Response Action | Element to be addressed |  | Development Plan (Task) | Ownership | Timescale for completion
|  |  | Assessment Grid PI GRADE |  |  | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
P-1 | National response plan for nuclear security event is in place | Policy | 0 | Incorporate nuclear security elements into the national response plan for emergencies | NSC
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
P-X | Additional written comments: | Policy | 0
|  | Procedures | 0
|  | Organization | 0
|  | Logistics | 0
|  | Infrastructure | 0
|  | Equipment | 0
|  | Personnel | 0
|  | Information | 0
|  | Training | 0
CDP: National Response Plan for Nuclear Security Events
Note on AB2: Any comment on dates or reference to an annex confirming dates later that 2020

## CDP
Timescale for completion
No. | Response Action | Element to be addressed | Development Plan (Task) | Ownership | 1Q 2016 | 2Q 2016 | 3Q 2016 | 4Q 2016 | 1Q 2017 | 2Q 2017 | 3Q 2017 | 4Q 2017 | 1Q 2018 | 2Q 2018 | 3Q 2018 | 4Q 2018 | 1Q 2019 | 2Q 2019 | 3Q 2019 | 4Q 2019 | 1Q 2020 | 2Q 2020 | 3Q 2020 | 4Q 2020 | Comment
O-1 | All agencies to be involved in response to NSE identified | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
O-2 | Lead organization designated | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
O-3 | Roles and responsibilities assigned | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
O-4 | Relations between all competent authorities involved in response to NSE are defined through formal protocols (e.g. written agreements or memoranda of understanding) including policy/strategic, tactical and operational levels [4.15, 4.17] | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
O-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
IG-1 | Collect information about material, adversary and/or target. | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
IG-2 | Confirm nuclear material inventory / radioactive material registry. | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
IG-3 | Gather relevant intelligence | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
IG-4 | Confirm nuclear material inventory / radioactive material registry. | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
IG-5 | Gather relevant intelligence | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
IG-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-1 | Activate response plan (National) | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-2 | Notify relevant organizations | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-3 | Activate relevant organizations | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-4 | Establish multi-agency integrated response command structure at all levels (strategic, tactical and operational levels). | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-5 | Deploy appropriate resources | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-6 | Create and share situational awareness for all response organizations | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-7 | Request international cooperation and assistance as necessary | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
NA-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
I-1 | Disruption of an ongoing NSE | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
I-2 | Render safe the device (as applicable) | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
I-3 | Obtain functional control of material and threat components | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
I-4 | Reinforce security measures at strategic locations | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
I-5 | Take necessary steps to gain control of seized material | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
I-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-1 | Collect evidence associated with NSE | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-2 | Radiological Crime Scene Management | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-3 | Expert witness testimony | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-4 | Maintain evidential integrity | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-5 | Ensure chain of custody for all evidence | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-6 | Conduct Conventional and nuclear forensics | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-7 | Support prosecution. | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CI-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
PI-1 | Release information to the public [17, 18]. | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
PI-2 | Gather information from the public | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
PI-3 | Provide advice to the public | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
PI-4 | Reassure the public | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
PI-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CM-1 | Package, transport and store nuclear and radioactive material | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CM-2 | Restore normality | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CM-3 | Restrict public access to scene(s) | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
CM-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
P-1 | National response plan for nuclear security event | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
P-X | Additional written comments: | Policy
Procedures
Organization
Logistics
Infrastructure
Equipment
Personnel
Information
Training
Capability Development Plan
Note on Z2: Any comment on dates or reference to an annex confirming dates later that 2020